## Summary
DATASIFT REHAB COST ESTIMATOR
Property: 5532 Joyce Ann Dr, Dayton, OH 45415
Local Pricing: Dayton, OH (Cost Index: 0.82x)
Property Details
Square Footage | 1,892 SF
Bed/Bath | 3 bed / 2.0 bath
Year Built | 1961
Property Type | Single Family - Brick Ranch
Condition | Dated cosmetic condition. Kitchen and baths need full remodel. Flooring worn throughout. HVAC furnace is new (2024), but A/C condenser is original R-22 unit. Electrical panel is breaker (not fuse), adequate. Roof noted as poor condition. Structure is solid brick.
Comp Reference
ARV (After Repair Value) | $265,000
Purchase Price | $155,000
Bucket A PPSF (Unrenovated) | $125.03
Bucket B PPSF (Renovated) | $156.35
Renovation Premium | 20.4%
Market Premium ($) | $59,258
Cost Estimate Comparison
Metric | Full Rehab | Wholetail
Scope | Full Rehab | Wholetail
Finish Tier | Investor-Flip Grade (Tier 3) | Builder to Mid Grade
Estimate | 63379 | 11358
Cost/SF | 33.5 | 6
Contingency | 10% | 5%
Deal Analysis
Metric | Full Rehab | Wholetail
ARV | 265000 | 265000
Purchase Price | 155000 | 155000
Rehab Cost | 63379 | 11358
Total Investment | 218379 | 166358
Potential Profit | 46621 | 48642
ROI | 21.3% | 29.2%
75% Rule MAO | 135371 | N/A
Recommendations
• Wholetail may offer BETTER ROI than full rehab on this deal. At ~$11K wholetail cost vs ~$63K full rehab, the wholetail route produces similar gross profit ($49K vs $47K) with far less risk, time, and capital deployed. Consider wholetail exit at $205-215K.
• Roof needs professional inspection before closing. Inspector rated it Poor (10+ years). Budget $6,000-9,000 for replacement (15-20 squares) if needed — this would be a separate line item above the contractor SOW.
• Verify window count with on-site walkthrough. Estimate assumes 15 windows; actual count may be higher (calibration data from a similar deal showed 17). Each additional window adds $550.
• The A/C condenser (R-22) MUST be replaced regardless of exit strategy. R-22 refrigerant is no longer manufactured and the system cannot be legally recharged. Budget $2,800.
• New furnace (2024) is a strong selling point for either exit strategy. Highlight in listing.
• GLA discrepancy between sources (1,652 vs 1,892 sqft). If actual GLA is closer to 1,652, reduce ARV to ~$240K. Verify with Montgomery County Auditor.

## Full Rehab Estimate
DATASIFT FULL REHAB ESTIMATE
Local Pricing: Dayton, OH ¦ Multiplier: 0.82x National
Property: 5532 Joyce Ann Dr ¦ 1,892 SF ¦ Finish: Investor-Flip Grade (Tier 3)
Mark "X" in Include column to add item to estimate. Totals auto-calculate.
Repair Item | Include? | Qty | Unit | $/Unit | Total | Notes
DEMO & CLEANUP
Full house interior demo | X | 1 | EA | 2500 | 2500 | Strip all flooring, fixtures, cabinets, prep for renovation
30-yard dumpster | X | 2 | EA | 530 | 1060 | Full renovation waste removal
Demo & Cleanup Subtotal |  |  |  |  | 3560
PAINT
Interior paint — all-in (walls + trim + ceiling) | X | 2100 | SF | 2.95 | 6195 | Single rate per paintable wall SF. Agreeable Gray walls, Extra White trim.
Primer (stain block) | X | 800 | SF | 2 | 1600 | Dark accent walls and stain-prone areas only
Paint Subtotal |  |  |  |  | 7795
FLOORING
LVP — Lifeproof (living, dining, kitchen, halls) | X | 1100 | SF | 5.5 | 6050 | Installed with underlayment. 10% waste factor included.
Carpet — bedrooms (with pad) | X | 480 | SF | 4.25 | 2040 | 3 bedrooms, standard plush carpet
Flooring Subtotal |  |  |  |  | 8090
KITCHEN
Cabinets — rip & replace (14-unit, white shaker) | X | 1 | EA | 4550 | 4550 | Soft-close, stock shaker cabinets
Granite countertop (Level 1) | X | 44 | SF | 50 | 2200 | Installed, includes cutouts and edge
Backsplash — subway tile | X | 40 | SF | 12 | 480 | White 3x6 subway, installed
Kitchen faucet (pull-down) | X | 1 | EA | 209 | 209 | Matte black or brushed nickel
Kitchen sink (SS undermount) | X | 1 | EA | 151 | 151 | Single-bowl stainless steel
Garbage disposal (1/2 HP) | X | 1 | EA | 250 | 250 | InSinkErator or equivalent
Cabinet hardware (pulls & knobs) | X | 28 | EA | 6 | 168 | Matte black bin pulls and knobs
Kitchen Subtotal |  |  |  |  | 8008
BATHROOMS
Full bath renovation (hall bath) | X | 1 | EA | 4000 | 4000 | New vanity, toilet, tub surround, tile floor, fixtures
Full bath renovation (master bath) | X | 1 | EA | 4000 | 4000 | New vanity, toilet, shower refresh, tile floor, fixtures
Hall bath ceiling repair (water damage) | X | 1 | EA | 500 | 500 | Remove OSB patches, hang new drywall, tape, mud, finish
Bathrooms Subtotal |  |  |  |  | 8500
WINDOWS & DOORS
Vinyl replacement windows | X | 15 | EA | 550 | 8250 | Double-hung, energy efficient. Count from inspection photos.
Interior door slabs (replace damaged) | X | 2 | EA | 220 | 440 | Only doors with visible damage
Door hardware — levers (all interior) | X | 10 | EA | 60 | 600 | Matching matte black or brushed nickel
Smart key locks (exterior) | X | 2 | EA | 75 | 150 | Front door + garage entry
Bypass closet door set | X | 1 | EA | 335 | 335 | Replace 1 damaged bifold with bypass
Windows & Doors Subtotal |  |  |  |  | 9775
ELECTRICAL
Outlets/switches — per room | X | 6 | RM | 100 | 600 | Replace all outlets + switches in renovated rooms
Flush mount light fixtures (matte black) | X | 8 | EA | 77 | 616 | Modern flush mount, interior rooms + halls
Exterior motion lights | X | 2 | EA | 110 | 220 | Motion-activated, front and rear
Smoke alarms (battery) | X | 4 | EA | 30 | 120 | Code compliance — all bedrooms + hallway
Electrical Subtotal |  |  |  |  | 1556
DRYWALL
Drywall patches (punch repair) | X | 3 | EA | 250 | 750 | Wall damage throughout — repair, tape, mud, texture match
Drywall Subtotal |  |  |  |  | 750
TRIM & MILLWORK
Shoe mold (at new flooring transitions) | X | 250 | LF | 1.35 | 338 | Where new LVP meets wall in renovated rooms
Baseboard — replace damaged sections | X | 100 | LF | 2.7 | 270 | Only visibly damaged areas, 3.25in MDF
Trim & Millwork Subtotal |  |  |  |  | 608
HVAC
A/C condenser — replace (R-22 to R-410A) | X | 1 | EA | 2800 | 2800 | R-22 refrigerant phased out. Existing unit cannot be serviced. Furnace is new (2024) — no work needed.
HVAC Subtotal |  |  |  |  | 2800
APPLIANCES
SS Refrigerator | X | 1 | EA | 1400 | 1400 | Stainless steel, standard size
SS Dishwasher | X | 1 | EA | 550 | 550 | No existing dishwasher — new install
SS Range/Stove | X | 1 | EA | 700 | 700 | Gas or electric per existing hookup
SS Microwave (over-the-range) | X | 1 | EA | 300 | 300 | Stainless, vented
Appliances Subtotal |  |  |  |  | 2950
EXTERIOR
Tuckpointing (brick repair) | X | 1 | EA | 325 | 325 | Spot repair where mortar is deteriorated
Gutter repair | X | 1 | EA | 125 | 125 | Repair damaged sections
Soffit repairs (major) | X | 1 | EA | 800 | 800 | Multiple sections with damage
Paint front step | X | 1 | EA | 50 | 50 | Curb appeal touch-up
Paint exterior door | X | 1 | EA | 125 | 125 | Front entry door refresh
Exterior Subtotal |  |  |  |  | 1425
LANDSCAPING & CLEANUP
Basic cleanup & mulch | X | 1 | EA | 500 | 500 | Trim, edge beds, fresh mulch
Power wash (house + concrete) | X | 1 | EA | 300 | 300 | Full exterior, driveway, walkways
Post-renovation cleanup | X | 1 | EA | 1000 | 1000 | Professional construction cleanup
Landscaping & Cleanup Subtotal |  |  |  |  | 1800
ESTIMATE TOTALS
Subtotal |  |  |  |  | 57617
Contingency (10%) |  |  |  |  | 5762
GRAND TOTAL |  |  |  |  | 63379
Cost per SF |  |  |  |  | 33.5

## Wholetail Estimate
DATASIFT WHOLETAIL ESTIMATE
Local Pricing: Dayton, OH ¦ Multiplier: 0.82x National
Property: 5532 Joyce Ann Dr ¦ 1,892 SF ¦ Finish: Builder to Mid Grade
Mark "X" in Include column to add item to estimate. Totals auto-calculate.
Repair Item | Include? | Qty | Unit | $/Unit | Total | Notes
PAINT
Interior paint — single neutral color (walls + trim) | X | 2100 | SF | 2.5 | 5250 | One coat, single neutral color throughout. Biggest ROI item for wholetail.
Paint Subtotal |  |  |  |  | 5250
FLOORING
LVP — worst areas only (kitchen, main hall) | X | 400 | SF | 5.5 | 2200 | Only where flooring is visibly damaged/stained
Carpet deep clean (bedrooms) | X | 480 | SF | 0.4 | 192 | Professional steam clean existing carpet
Flooring Subtotal |  |  |  |  | 2392
BATHROOMS
Bathroom clean, caulk, minor repairs | X | 2 | EA | 400 | 800 | Deep clean, fresh caulk, tighten fixtures. No remodel.
Hall bath ceiling drywall repair | X | 1 | EA | 500 | 500 | Remove OSB patches, proper drywall repair — safety/appearance issue
Bathrooms Subtotal |  |  |  |  | 1300
DRYWALL
Drywall patches (visible holes only) | X | 3 | EA | 150 | 450 | Quick patch visible damage only
Drywall Subtotal |  |  |  |  | 450
EXTERIOR
Tuckpointing (brick repair) | X | 1 | EA | 325 | 325 | Safety and appearance
Paint front step | X | 1 | EA | 50 | 50 | Quick curb appeal fix
Exterior Subtotal |  |  |  |  | 375
LANDSCAPING & CLEANUP
Deep clean (full house) | X | 1 | EA | 500 | 500 | Professional cleaning — this is where wholetail magic happens
Power wash (house + concrete) | X | 1 | EA | 300 | 300 | Exterior, driveway, walkways
Mow, trim, basic landscaping | X | 1 | EA | 250 | 250 | Basic curb appeal
Landscaping & Cleanup Subtotal |  |  |  |  | 1050
ESTIMATE TOTALS
Subtotal |  |  |  |  | 10817
Contingency (5%) |  |  |  |  | 541
GRAND TOTAL |  |  |  |  | 11358
Cost per SF |  |  |  |  | 6

## Condition Assessment
PROPERTY CONDITION ASSESSMENT
5532 Joyce Ann Dr, Dayton, OH 45415
Category | Item | Condition | Notes | Rehab Action | Wholetail Action
EXTERIOR
| Roof (Shingle) | Poor | 10+ years old, inspector rated Poor. Needs professional inspection. | Budget for replacement (separate from contractor SOW) | Inspect; repair if actively leaking
| Brick Siding | Good | Solid brick ranch, minor tuckpointing needed in spots | Tuckpointing repair | Tuckpointing repair
| Windows (Vinyl) | Fair | Vinyl windows, functional but dated. No visible failures or fogging. | Replace all windows for energy efficiency and curb appeal | Leave as-is unless broken
| Gutters | Fair | Present and functional, some sections need repair | Repair damaged sections | No action needed
| Soffit/Fascia | Fair | Some displaced vent covers, soffit damage visible at base | Soffit repairs | No action needed
| Fence (Wood) | Fair | Aging wooden privacy fence, functional but showing wear | Leave as-is (not a deal-killer) | Leave as-is
| Landscaping | Fair | Overgrown, needs cleanup and mulch | Cleanup, mulch, edge, power wash | Mow, trim, power wash
KITCHEN
| Cabinets | Poor | Original 1960s cabinets, very dated. Not salvageable for a flip. | Full rip & replace with white shaker | Clean only
| Countertops (Formica) | Poor | Original laminate/Formica countertops, dated and worn | Replace with granite | Leave as-is
| Appliances | Poor | Dated appliances, no dishwasher installed | Full SS appliance package (fridge, stove, DW, microwave) | Clean existing; leave as-is
| Flooring | Poor | Dated kitchen flooring, worn | LVP throughout | LVP if badly damaged
LIVING AREAS
| Flooring (Parquet/Mixed) | Poor | Worn parquet flooring in living areas, showing significant wear | LVP throughout main living areas | LVP in worst areas only
| Walls/Paint | Poor | Dark accent walls, dated colors, wall damage and cracks visible | Full repaint (Agreeable Gray) | Full repaint (single neutral)
| Ceilings | Fair | Textured/popcorn ceilings with visible cracks in some areas | Paint over (removal too expensive for ROI in this market) | Leave as-is
| Light Fixtures | Poor | Dated ceiling fans, brass fixtures, dome lights throughout | Replace all with modern flush mounts | Leave as-is
| Window Treatments | Poor | Vertical blinds, dated | Remove (leave windows bare for showing) | Leave as-is
BEDROOMS
| Flooring (Carpet/Parquet) | Fair | Mix of worn carpet and parquet in bedrooms | New carpet in all bedrooms | Deep clean existing carpet
| Closet Doors (Bifold) | Fair | Dated bifold closet doors, functional | Replace 1 damaged set with bypass | Leave as-is
| Walls/Paint | Fair | Dated paint, some wall damage | Included in whole-house repaint | Included in whole-house repaint
BATHROOMS
| Hall Bathroom | Poor | Dated vanity, dated tile, ceiling has OSB patches from water damage repair. Pink fixtures. | Full renovation + ceiling drywall repair | Clean, caulk, fix ceiling drywall
| Master Bathroom | Poor | Dated vanity, stained tub/shower, dated fixtures and tile | Full renovation | Deep clean, caulk, minor repairs
MECHANICAL
| Furnace | Good | NEW — Butler Heating installed 8/8/2024. Do NOT scope. | No action — new unit | No action — new unit
| A/C Condenser | Poor | Original R-22 unit, refrigerant phased out. Must replace. | Replace with new R-410A condenser | Replace (R-22 is a liability)
| Water Heater | Good | Envirotemp 40-gal, ~2 years old (2024). Functional. | No action — relatively new | No action
| Electrical Panel | Fair | Breaker panel (not fuse box), original 1959 circuit directory. Adequate for current use. | No panel upgrade needed; update outlets/switches per room | No action
| Plumbing | Good | Copper supply lines visible, no issues noted | No action needed | No action needed
INTERIOR
| Interior Doors | Fair | Mix of hollow-core doors, some showing wear. Most functional. | Replace 2 damaged slabs, new hardware all doors | Leave as-is
| Trim/Baseboard | Fair | Original trim, mostly intact. Some damage where flooring meets wall. | Shoe mold at new flooring, replace damaged baseboard sections | Leave as-is
| Drywall | Fair | Several punch holes and damage spots throughout. Hall bath ceiling has major repair needed. | Patch all damage, repair hall bath ceiling | Patch visible holes, repair hall bath ceiling

## Deal Analyzer
DEAL ANALYZER
PROPERTY INFORMATION
Address | 5532 Joyce Ann Dr
City/State/Zip | Dayton, OH 45415
Square Footage | 1,892
Beds/Baths | 3 / 2.0
Year Built | 1961
FULL REHAB ANALYSIS |  | WHOLETAIL ANALYSIS
After Repair Value (ARV) | 265000 | After Repair Value (ARV) | 265000
Purchase Price | 155000 | Purchase Price | 155000
Rehab Cost | 63379 | Rehab Cost | 11358
Total Investment | 218379 | Total Investment | 166358
Potential Profit | 46621 | Potential Profit | 48642
ROI | 21.3% | ROI | 29.2%
75% RULE CHECK
Max Allowable Offer (75% Rule) | 135371
Formula: ARV × 75% − Rehab Cost
REHAB BUDGET vs MARKET PREMIUM
Market Premium (Bucket B − A × GLA) | 59258
Rehab as % of Premium | 107%
Target: 40-70% (healthy margin)

## Budget Tracker
BUDGET TRACKER
Track actual costs against budget during renovation
# | Line Item | Budget | Actual | Variance | Invoice Date | Paid Date | Notes
1 | Demo & Cleanup | 3560
2 | Paint | 7795
3 | Flooring | 8090
4 | Kitchen | 8008
5 | Bathrooms | 8500
6 | Windows & Doors | 9775
7 | Electrical | 1556
8 | Drywall | 750
9 | Trim & Millwork | 608
10 | HVAC | 2800
11 | Appliances | 2950
12 | Exterior | 1425
13 | Landscaping & Cleanup | 1800
14 | Contingency | 5762
TOTALS

## Material Specs
RECOMMENDED MATERIAL SPECIFICATIONS
Finish Tier: Investor-Flip Grade (Tier 3)
Item | Specification | Est. Price | Finish | SKU/Link | Alt. Option | Notes
FLOORING
LVP | Lifeproof Brand, 7mm+ thickness, waterproof core | $2.50-3.50/SF material | Gray-tone wood look | Home Depot — Lifeproof Sterling Oak or similar | TrafficMaster Rigid Core | Most popular flip flooring in Midwest markets
Carpet | Mohawk or Shaw, 30-40oz face weight, stain resistant | $1.50-2.50/SF material | Neutral beige/gray | Home Depot/Lowe's builder grade | Lifeproof Pet Proof | Bedrooms only
KITCHEN
Cabinets | White shaker, plywood box, soft-close hinges/drawers | $150-250/LF | White or light gray | Hampton Bay Shaker or equivalent RTA | IKEA SEKTION | Stock cabinets keep cost down while looking custom
Countertops | Level 1 Granite, 3cm thickness, eased edge | $50/SF installed | White/gray veined (Luna Pearl, White Dallas) | Floor & Decor or local fabricator | Quartz (MSI or Silestone) | Granite is popular in Dayton market per comps
Backsplash | Ceramic subway tile, 3x6, beveled edge | $1.50-3.00/SF material | White gloss or matte | Floor & Decor or Home Depot | Peel & stick for wholetail | Standard subway is timeless and affordable
PAINT
Interior Walls | Sherwin-Williams SuperPaint or equivalent, flat/eggshell | $45-55/gallon | Agreeable Gray (SW 7029) | SW 7029 | BM Revere Pewter | Most universally appealing neutral
Trim & Doors | Sherwin-Williams ProClassic, semi-gloss | $55-65/gallon | Extra White (SW 7006) | SW 7006 | BM Chantilly Lace | Semi-gloss for durability and clean look
FIXTURES
Light Fixtures | Flush mount, LED integrated or E26 base | $25-50/EA | Matte black | Home Depot — Hampton Bay or Globe Electric | Brushed nickel | Matte black trending in 2025-2026
Door Hardware | Passage/privacy levers | $15-25/EA | Matte black or brushed nickel (match lights) | Kwikset Halifax or Schlage | Defiant brand (budget) | Match finish to light fixtures for cohesive look
PAINT COLOR SCHEME (Modern Neutral — Most Popular)
Application | Color Name | Brand | Code
Interior Walls | Agreeable Gray | Sherwin-Williams | SW 7029
Trim & Doors | Extra White | Sherwin-Williams | SW 7006
Ceilings | Ceiling Bright White | Sherwin-Williams | SW 7007
Cabinets | Pure White | Sherwin-Williams | SW 7005
Accent | Iron Ore | Sherwin-Williams | SW 7069
Exterior | Repose Gray | Sherwin-Williams | SW 7015

## Project Checklist
PROJECT CHECKLIST & TIMELINE
Task | Status | Due Date | Completed | Assigned To | Notes
PRE-CONSTRUCTION
Turn on utilities (water, electric, gas) | Not Started
Property inspection / scope walkthrough | Not Started
Finalize scope of work | Not Started
Get contractor bids (minimum 2-3) | Not Started
Pull required permits | Not Started
Order materials (long lead items first) | Not Started
Schedule dumpster delivery | Not Started
Secure property (locks, lockbox) | Not Started
WEEK 1 — DEMO & ROUGH
Dumpster delivered | Not Started
Interior demo (kitchen, bath, flooring) | Not Started
Rough plumbing | Not Started
Rough electrical | Not Started
HVAC rough-in / replacement | Not Started
Framing changes (if any) | Not Started
Schedule rough inspections | Not Started
WEEK 2 — SYSTEMS & STRUCTURE
Rough inspections passed | Not Started
Insulation | Not Started
Drywall hang + tape + mud | Not Started
Window installation (if replacing) | Not Started
Exterior repairs (siding, soffit, fascia) | Not Started
Roof work (if needed) | Not Started
WEEK 3 — FINISHES
Drywall sanding + prime | Not Started
Paint — primer coat | Not Started
Paint — finish coats (walls + ceilings) | Not Started
Flooring installation | Not Started
Cabinet installation | Not Started
Tile work (bathrooms, backsplash) | Not Started
WEEK 4 — FIXTURES & DETAILS
Countertop installation | Not Started
Plumbing fixtures (faucets, toilets, sinks) | Not Started
Electrical fixtures (lights, outlets, switches) | Not Started
Appliance installation | Not Started
Door hardware | Not Started
Backsplash completion | Not Started
Paint touch-up (all trim, doors) | Not Started
WEEK 5 — PUNCH LIST & CLOSE OUT
Final walkthrough with contractor | Not Started
Punch list items addressed | Not Started
Final inspections (building, mechanical) | Not Started
Carpet installation (if applicable) | Not Started
Deep cleaning (professional) | Not Started
Landscaping / curb appeal | Not Started
LISTING PREPARATION
Staging (furniture + decor) | Not Started
Professional photography | Not Started
Listing prep (description, disclosures) | Not Started
Schedule open house | Not Started
MLS listing live | Not Started
Lockbox for showings | Not Started